## Suppliers
MODULAR ALL DRIVES - Supplier Contact Tracker ¦ Aluizio Kleine / Industrial Engineering / WEG Drives and Controls ¦ Updated: 30/06/2026
Region | Supplier | Contact Name(s) | Email(s) | Outreach Status | Meeting Date | Pugh Rank | Quote / Next Step | Notes
BRASIL | Bosch (Campinas/Curitiba) | Marcelo Laranjeira (Commercial) Victor Souza (Test Electrical) | Marcelo.Laranjeira@br.bosch.com Souza Victor (CaP/MFI31) <Victor.Souza@br.bosch.com> | MET | 17/06/2026 | 3rd (datum) | Waiting for WEG docs: test prescriptions + product dimensions table + terminal drawings | BEST local support. 60+ yrs. Exclusive WEG Automacao contract (>1M WEG products/yr). Own supervisory SW. 24/7 call center. ECU assembly+test experience (closest analog to VFD). Pugh datum.
| Autec |  | projetos@autecjoi.com.br | MET | 15/06/2026 | 5th (-11) | Waiting for quotation | Local company in Jaragua do Sul area. Geographical advantage. Electrical test competence TBD.
| Mondragon Assembly |  | f.dasilveira@mondragon-assembly.com | MET | 16/06/2026 | - | Waiting for quotation | Assembly and test lines for electronics. Local Brazil operation. Tier S supplier.
| Aumaq |  | vendas@aumaqrs.com.br | EMAIL SENT | - | - | Waiting for reply | Email sent.
| SPI |  | info@integradora.com.br | EMAIL SENT | - | - | Waiting for reply | Email sent.
| MCK Automacao |  | vendas@mckautomacao.com.br | EMAIL SENT | - | - | Waiting for reply | Email sent.
EUROPE | MASMEC | Stefano Piccinno (Sales Engineer) Luigi Di Leo | info@masmec.com Stefano Piccinno <stefano.piccinno@masmec.com> Luigi Di Leo <luigi.dileo@masmec.com> Stefano De Benedictis <stefano.debenedictis@masmec.com> | MET | 16/06/2026 | 5th (-11) | Waiting for quotation. WEG to send: test prescription per module + confirm WEG PLC (not Siemens) | Bari, Italy. Direct experience testing automotive inverters (hipot, functional, load). Bosch Rexroth TS2 conveyor. Brazil installs. All machines made in Italy. Digital twin w/ Plant Simulation.
| Comau |  | Carla Cristina Haddad <carla.cristina@comau.com> Claudio Ragassi Moneda <claudio.moneda@comau.com> | DECLINED | 11/06/2026 | 2nd (+1) | OUT - Declined 23/06/2026 | DECLINED (23/06/2026, Carla Cristina Haddad, Sales Coordinator - carla.cristina@comau.com): Unavailability of qualified workforce to absorb responsibilities beyond current and planned ones; high competitiveness required for this specific activity; challenging deadlines. Reiterated strong interest in future opportunities and remains open to new contacts that better fit Comau's resource allocation and expertise. Large automotive machine builder. Brazil presence (Betim/MG). PE-owned (One Equity Partners).
| Hahn Automation |  | enviado via site | EMAIL SENT | - | - | Waiting for reply | Email sent via website.
| ATS Corporation |  | solutions@atsautomation.com | EMAIL SENT | - | - | Waiting for reply | Email sent.
| FFT Produktionssysteme | Edgar Vöhringer (Account Manager) | info@fft.de Edgar Vöhringer <edgar.voehringer@fft.de> | MET | 24/06/2026 | - | Sent test specification + 3D CAD and scope changes (26/06/2026). Medium Drives scope to follow this week. Next: await FFT feedback / schedule follow-up call. | Fulda, Germany (Edgar Vöhringer). INBOUND contact. Meeting held 24/06/2026. Scope changes communicated: (1) Hipot + Functional tests merged into a SINGLE module; (2) Power connection separated from Control/IO - hipot uses only power connections, functional uses power + control; (3) Semi-automated product-to-pallet connection (busbars/needles/pogo - method TBD by supplier), connection movement & fixturing by operator; (4) Visual inspection limited to verifying the HMI is working correctly. Test specification + 3D CAD sent. Medium Drives scope (higher power/current/size) to be sent this week.
USA | DMC | Brent Hoerman (Senior Eng. Manager) Neal Walters (Mech. Eng. Lead) Aleks Konstantinovic (Automation Eng.) | email.sales@dmcinfo.com; <Brent.Hoerman@dmcinfo.com> | MET | 17/06/2026 | 8th (-20) | Waiting for quotation (after Jul 4th holiday). WEG to send: CAD/connector drawing of product | Chicago. ~250-300 engineers. T&M + Manufacturing Automation. C#/Java/Python confirmed (no LabVIEW). FAT Chicago, fly to Brazil for SAT. No Brazil office.
| JR Automation (Hitachi) |  | solutions@jrautomation.com | DECLINED | - | - | OUT - Declined | DECLINED: will not support in Brazil.
| Develop LLC | Matt Moseman (Sales) | sales@develop-llc.com | DISQUALIFIED | 15/06/2026 | 4th (-10) | OUT - Disqualification email sent 18/06/2026 | DISQUALIFIED: North America only - cannot commission or support in Brazil. WEG has no US facility for SAT. Strong technical fit; worth revisiting for future USA/Canada plant expansion.
| Eclipse Automation |  | enviado via site | EMAIL SENT | - | - | Waiting for reply | Email sent via website.
| iAutomation |  | customerrelations@i-automation.com | EMAIL SENT | - | - | Waiting for reply | Email sent.
| Acieta |  | enviado via site | EMAIL SENT | - | - | Waiting for reply | Email sent via website.
| The Morse Group |  | enviado via site | EMAIL SENT | - | - | Waiting for reply | Email sent via website.
CHINA | BBS Automation (Suzhou) | Ma Vivian (Commercial/Account) Liu Carlson (Technical) | info@bbsautomation.com info.suzhou@bbsautomation.com Ma, Vivian <Vivian.Ma@bbsautomation.com> Huang, Jack <jack.huang@bbsautomation.com> | MET | 17/06/2026 | 1st (+8) | Waiting for quotation. Send: test spec + assembly scope (Alissonn). Provide WEG invitation letter for visa when needed. | Part of Dual Group (acquired 2023). HQ Munich. 4 China factories (Suzhou, Tianjin, Kunshan, Xian). ~EUR 200M revenue China. BEST reference: inverter EOL test + PCB/IGBT assembly. WEG PLC: never used - checking. Team Soft (C#) available.
| PIA Automation (Suzhou) | Wang Abel Xiang Cui David Qingjun | Lu Jacky Jian <Jian.Lu@piagroup.com> Cui David Qingjun <qingjun.cui@piagroup.com> Wang Abel Xiang <Xiang.Wang@piagroup.com> | MET | 18/06/2026 | 7th (-15) | Waiting for quotation (~next week after holiday). WEG to send: product images + test specification | Brazil commissioning CONFIRMED (project near Brazilian capital). Short first meeting. HMI test NOT required (PLC via RS485/Modbus). PLC: WEG preferred but flexible.
| CASMT |  | info@casmt.com | EMAIL SENT | - | - | Waiting for reply | Email sent.
| Ronstein |  | Sales@Ronstein.com | EMAIL SENT | - | - | Waiting for reply | Email sent.
| Harmontronics |  | info.cn@htsm.com | EMAIL SENT | - | - | Waiting for reply | Email sent.
JAPAN | Tamadic |  | prir@tamadic.co.jp Fubei Lyu <lv-fubei@tamadic.co.jp> | DECLINED | 24/06/2026 | - | OUT - Declined 24/06/2026 | DECLINED (24/06/2026, Fubei Lyu): No established support structure in Brazil; engineering/project support focused on Japan, China, USA. Standard business practice for overseas customers requires cooperation through a Japanese trading company, which makes the current project framework challenging. Open to future collaboration for projects in Japan, China, USA, or other Asia / North America locations.
| Tokyo Densei |  | enviado via site | EMAIL SENT | - | - | Waiting for reply | Email sent via website.
LEGEND
MET - Meeting held, active in process
EMAIL SENT - Awaiting reply
DECLINED / DISQUALIFIED - Out of process