Supplier Meeting Summary

Modular All Drives — EOL Test System | BBS Automation (China)

| Supplier | BBS Automation — Suzhou, China (part of Dürr Group since 2023) |
| --- | --- |
| Date / Duration | 17 June 2026, 07:00 (BRT) — 1 h 25 min |
| Meeting type | First discovery call — company presentation, capability review & concept walkthrough |
| BBS attendees | Vivian Ma (Key Account Manager); Carlson Liu (Sales / Project) |
| WEG attendees | Aluizio Kirschner & Raphael Franklim (Industrial Engineering); Júlio Cesar Pedroso; Alissonn Felippe Bebber (assembly line) |

# Executive Summary

BBS presented as a large global automation group (now part of Dürr), with ~20,500 employees worldwide, HQ in Munich, and a strong China operation (~950 staff, ~€200M revenue, 22 years' history, plants in Suzhou, Tianjin, Kunshan). They cover the entire production process — assembly automation and test automation — and showed an extensive portfolio of automotive electrification references (motor/stator, inverters/controllers, BMS, battery packs) including PCB-to-IGBT press-fit assembly and EOL electrical test lines. Their former testing brand teamtechnik is now part of the group, adding test-bench depth.

Overall fit: Very strong technically — arguably the broadest demonstrated experience in VFD/inverter assembly + EOL test of any supplier so far. Main open points: no WEG-PLC experience, default to LabVIEW (WEG wants C#/Java/Python open source), no Brazil presence, and an explicit concern about current capacity to meet the timeline.

# Company Profile (as presented)

- BBS = "Best Business Solution"; acquired by Dürr Group in 2023. Dürr's three pillars: paint shops / final assembly / test systems; industrial automation (incl. Schenck balancing, battery production tech); woodworking (Homag).

- Global footprint: ~20 sites, ~20,500 employees; factories in Europe, USA, Mexico, India (Pune), Malaysia, and China. Suzhou HQ office reportedly closed last month — now four China sites.

- BBS China: ~950 employees, ~€200M revenue. Engineering depth cited: ~240 mechanical, 200+ electrical/test, 25 application, 50+ project management, 30+ service engineers.

- Design tools: AutoCAD, SolidWorks, in-house PDM, Visual Components simulation, E-plan; PLC mainly Siemens (also Rockwell, Beckhoff).

- Certifications: ISO, VDA 6.3, IATF (automotive). In-house machine building at Suzhou, Tianjin, Kunshan; 24-hour service hotline.

- Strong digitalization: logistics & process simulation (Visual Components), virtual commissioning to debug PLC code before build.

# Capability Assessment Against Scope

| Requirement | Assessment | Notes |
| --- | --- | --- |
| VFD / inverter EOL electrical test (hipot / functional / load) | Strong | Demonstrated EOL test lines for inverters/controllers including HV, LV and function test. Former teamtechnik brand adds dedicated tester expertise. Carlson is not the test engineer — detailed test discussion to follow with their experts. |
| Full inverter / controller assembly incl. PCB handling | Strong | Showed controller (inverter) assembly+test lines with PCB press-fit onto IGBT, 'one-box' PDU/DCDC/OBC lines, BMS lines. Directly relevant to the separate assembly-line scope (Alissonn/Franklim). |
| Automated electrical connection (product→fixture & fixture→module) | Capable | Familiar with both approaches: workpiece carrier with common interface, or carrier+product entering the station for direct connection. Asked whether connection is cable or hard-connector. Accepts WEG's requirement that both be automated. |
| Conveyor / flow-through / modular expansion | Strong | Immediately understood the parallel-test, flow-through rationale (long test times). Uses Z-card / round-table / AGV solutions and modular separable stations in references. |
| Brazil commissioning & after-sales support | Risk | No current Brazil clients. Willing to travel (global company); needs WEG invitation letters for engineers. Vivian/Carlson to check production management and revert on support model. |
| Use of WEG components / WEG PLC | Partial risk | No WEG-brand experience. Other components OK; WEG PLC is the concern — to be checked with their electrical team (noted WEG's newest PLC uses CODESYS, which may ease integration). |
| Test software ownership / language | Risk | Default is LabVIEW; teamtechnik 'TeamSoft' (C-based) available but more expensive. WEG requires open-source C#/Java/Python — BBS confirmed C# possible but to be validated against cost/spec. |
| Capacity vs end-2027 timeline | Concern (BBS-flagged) | Carlson repeatedly flagged uncertainty about internal capacity for the requested timeline; to confirm after internal check. |

# Key Technical Points Aligned

- Each module to have its own conveyor so capacity grows by simply adding a module (no re-integration).

- Drive moves backward into a test position so the main conveyor stays free for parallel testing — BBS confirmed this matches their standard approach.

- Fixture→module connection standardized across all fixtures; product→fixture connection product-specific. Connection type (cable vs hard connector) left open for BBS to propose.

- Cycle times confirmed: hipot 3–60 s; functional 1.5–7 min; load 6–20 min — load test is the bottleneck; expect ~1 hipot + 1 functional feeding 3–5 load modules.

- Only the load module is heated (50 °C, no humidity control).

- Scope clarified as a modular platform (not a single line) covering many VFD variants — initially ~3 product types / up to ~5 fixture recipes; WEG to confirm exact variant count by email.

- Test software: collaboration model — BBS develops, WEG supplies the test know-how/routines.

# Commercial & Timeline

| WEG project deadline | Test + assembly lines commissioned in Brazil by end of 2027 |
| --- | --- |
| Purchase order target | WEG intends to place PO by end of 2026; supplier selection by July/Aug 2026 |
| Quote purpose | First quote is a budgetary target only — single lump-sum number, no cost breakdown, no layouts/datasheets required yet |
| Quotes requested | Three separate quotes: (1) testing line, (2) assembly + packaging line, (3) full line together |
| Quote scope (this stage) | Three test machines (1 hipot, 1 functional, 1 load) + conveyor; supplier to quote all components, WEG-component discount discussed later |
| Budget position | No fixed budget — evaluated on payback (as communicated to all suppliers) |
| Replication | Concept to be replicated to plants in China, Italy, Mexico, India |

# Action Items

| Owner | Action | Status |
| --- | --- | --- |
| WEG | Send confirmation of number of product variants / fixture recipes to be tested (Aluizio, by email). | Open |
| WEG | Provide invitation letters for BBS engineers to support commissioning/travel to Brazil. | Open |
| WEG | Forward the test specification / functional test sequence to BBS's test engineer for review. | Open |
| BBS | Internal capacity check against the end-2027 timeline and revert with feedback. | Open |
| BBS | Confirm WEG-PLC (CODESYS) compatibility with their electrical team. | Open |
| BBS | Prepare three budgetary quotes (testing / assembly / full line) as soon as possible. | Open |
| WEG (Assembly) | Alissonn & Franklim to send the assembly-line scope by email (handled as a separate project). | Open |

# Evaluation Notes

Positives

- Deepest demonstrated track record for inverter/controller EOL test + assembly, including PCB-to-IGBT press-fit — closely analogous to WEG's product.

- Full-process capability (assembly + test + packaging) under one global group; strong simulation and virtual commissioning.

- Immediately understood the modular, flow-through, parallel-test concept and engaged with practical solution options.

Watch points

- No WEG-PLC experience and a LabVIEW default — software language/ownership is a real gap vs WEG's open-source C#/Java/Python requirement.

- No Brazil footprint; support model and response time still undefined.

- BBS itself flagged capacity uncertainty for the timeline — track closely.

- 'Made in China' origin worth confirming for the final build location and any WEG sourcing/compliance considerations.

Prepared from the meeting transcript of 17 June 2026. Standard qualification questions applied for cross-supplier comparison.